## Sheet1
Date | Task no | Task | Task Description | Task Status | Time
2023-07-29 | 0 | Projects Displayed | Showed some of my projects related to web development | Ok | 5.00-6.11
2023-07-30 | 1 | Contact Form | Create a basic contact form and store the data in database | Completed | 5.00-6.10
2023-07-31 | 2 | SDLC for the Registration form/Project Discussion | Expained orally about some of the steps and their requirements and Project Discussion | Completed | 5.00-6.9
2023-08-01 | 3 | Radiant Enrollment Form | Location,lingual skills,References and experience yes/ no | Completed | 5.00-6.8
2023-08-02 | 4 | Enrollment form fields | Achievements and extra curricluar activtites,etc | Completed | 5.00-6.7
2023-08-03 | 5 | Next button for form | Trying out the next and previous button of the form-not taken further | Completed | 5.00-6.6
2023-08-04 | 6 | Admin Panel login and logout | the login,logout and the dashboard | Completed | 5.00-6.5
2023-08-05 | 7 | Rules Page | Rules and Regulation page to be designed with signature and date | Completed | 5.00-6.4
2023-08-06 | 8 | Experience table | Adding Js to the table if selected as yes then only display it | Completed | 5.00-6.3
2023-08-07 | 9 | Agree and continue checkbox | Agree and continue checkbox before submittion with validation | Completed | 5.00-6.2
2023-08-08 | 10 | Database and some change in ref | Created database for the whole form and added note for reference | Completed | 5.00-6.1
2023-08-09 | 11 | form addon | Added photo upload and Counsellers name to be selected | Completed | 5.00-6.0
2023-08-10 | 12 | Adding prefix for counsellers | Added mr and mrs titles for counsellers | Completed | 5.00-6.1
2023-08-11 | 13 | Generating pdf of the form | Made pdf but the fields where only displayed without actual form layout | Completed | 5.00-6.2
2023-08-12 | 14 | photo to be viewed in the box | upload box with the passport size photo to be fit into it | Completed | 5.00-6.3
2023-08-13 | 15 | Enrollment form pdf with the download button | created the pdf the tcpdf and fpdf but not completed correctly | Incomplete | 5.00-6.4
2023-08-14 | 16 | Create the print option same as ctrl+p | Created the same with the windows.print function and was proper | Completed | 5.00-6.5
2023-08-15 | 17 | Admin Panel View button for pdf | Created but is not fully complete as database fetching not proper | Incomplete | 5.00-6.6
2023-08-16 | 18 | pdf with Htmltocanvas | Created but the photo was not displayed | Completed | 5.00-6.7
2023-08-17 | 19 | pdf with Htmltocanvas | photo and signs displayed sucessfully | Completed | 5.00-6.8
2023-08-18 | 20 | pdf formatting | layout padding margin etc | Completed | 5.00-6.9
2023-08-22 | 21 | pdf with headers and footer | pdf with the header image and title and footer | Completed | 5.00-6.10
2023-08-23 | 22 | pdf completed with the toast | toast message of submittion successful | Completed | 5.00-6.11
2023-08-24 | 23 | Email Sending to Counsellers | Tried with the form submit but for only one email id working | Completed | 5.00-6.12
2023-08-25 | 24 | Email With a common mail id | Mail to be sent to counseller and user with a offical mail id | In Progress | 5.00-6.13
28-08-2023 to 31 -8 |  | Email | Email Send Using phpmailer and smtp server | Completed | 5.00-6.15
September Started
2023-09-01 | 25 | Responsive Form | Make the mobile view of the form responsive | in Progress | 5.00-6.16
2023-09-03 |  | Responsive Form |  | Completed | 5.00-6.17
2023-09-04 | 26 | Email Notification for user | Notification | Completed | 5.00-6.18
2023-09-05 | 27 | Email Forwarding to admin | forwarding the approved enrollment for further to the admin through mail | In Progress | 5.00-6.19
2023-09-06 | 28 | View Option in Admin Panel | view the student form submitted by the admin in admin dashboard | Completed | 5.00-5.45
2023-09-07 | 29 | download pdf option in admin panel | download pdf of the user enrollment form in admin dashboard | Completed | 5.00-5.45
2023-09-08 | 30 | Subadmins for admin panel | subadmins of all the counsellors in the admin panel with login and bucket system for forms of each | Completed | 5.00-6.00
2023-09-09 | 31 | photo to be viewed in the admin | photo and signs displayed in the amin panel for edit and view options | In Progress | 5.00-5.40
2023-09-11 | 32 | image size setting and alert message | setting photo and signature of the size 256kb or less and if not alert mssg | Completed | 5.00-5.45
2023-09-12 | 33 | page break for pdf and display photo | adding page breaks in the pdf downloaded and displaying images in admin | In Progress | 5.00-5.40
2023-09-13 |  | page break for pdf and display photo | adding page breaks in the pdf downloaded and displaying images in admin | Completed | 5.00-6.00
2023-09-14 | 34 | toast | Dispay toast of submittion sucessfully with download button | In Progress | 5.00-6.00
2023-09-15 |  | toast | dispay toast of submittion sucessfully with download button | not suceeded | 5.00-6.00
2023-09-16 | 35 | view Option in Admin Panel | some updates regarding the view of disabled and selections in payment modes | Completed | 5.00-5.40
2023-09-17 | 36 | submit button with two actions | submit button with the database submittion and the pdf download | not suceeded | 5.00-5.45
2023-09-18 | 37 | changes in web form final touch | some speling mistakes,tables required,size of photo,database etc | In Progress | 5.15-6.15
2023-09-20 |  | changes in web form final touch | some speling mistakes,tables required,size of photo,database etc | Completed | 5.00-6.15
2023-09-21 | 38 | submit button with two actions | submit button with the database submittion and the pdf download using ajax | in Progress | 5.00-5.45
2023-09-22 | 38 | submit button with two actions | submit button with the database submittion and the pdf download using ajax | Completed | 5.00-6.00
2023-09-23 | 40 | pdf modifications fromatting | pdf with the page break,padding and margin, name n all | Completed | 5.00-5.40
2023-09-25 | 41 | admin panel photo n signature | photo n signature in admin update and view options | In Progress | 5.00-5.30
2023-09-26 |  | admin panel photo n signature | photo n signature in admin update and view options | In Progress | 5.00-5.30
2023-09-29 | 42 | sweet toast on submit button | sweet toast added on form submittion using ajax for database and pdf downloading | Completed | 3.10-4.00
2023-09-30 |  | admin panel photo n signature | photo n signature in admin update and view options | Completed
1 Oct-6 Oct | 43 | Web Form and admin Final | Web Form Final changes with admin Image display with the update and view | Completed | 11.30-1.45
October Started -New Project
2023-10-10 | 1